## Sheet 1
Name | PM | Status | Total.Amount | Unpaid.Amount | Start.Date | End.Date | Tags | invoice.check..confirmation.received. | Deviation
aevum GmbH (libxml2) | Mirko | In progress | 136000 | Milestone #1,Milestone #3,Milestone #2,Milestone #4,Milestone #5,Milestone #6 | August 3, 2023 | December 31, 2024 | May23 | Yes
Centricular Ltd (Gstreamer RTP) | Mirko | In progress | 203000 | Milestone #1.1,Milestone #2.1,Milestone #3.1,Milestone #3.2,Milestone #3.3,Milestone #3.4,Milestone #3.5,Milestone #1.2,Milestone #3.6,Milestone #4.1 | October 2, 2023 | December 31, 2023 |  | No
Codethink (systemd) | Mirko | In progress | 455000 | Milestone #1,Milestone #2,Milestone #3,Milestone #4,Milestone #5 | September 14, 2023 | June 30, 2024 |  | No
Drupal Association (Drupal (2023)) | Mirko | In progress | 278700 | Milestone #A1,Milestone #A2,Milestone #A3,Milestone #A4,Milestone #B1,Milestone #B2,Milestone #B3,Milestone #B4,Milestone #B5 | October 2, 2023 | December 31, 2023 |  | No
FREEXIAN SARL (debusine) | Tara | In progress | 485200 | debusine Milestone 1,debusine Milestone 2,debusine Milestone 3,debusine Milestone 4,debusine Milestone 5 | September 28, 2023 | December 31, 2024 |  | Yes | Check back in December, 80k
GNOME Foundation (GNOME Project) | Tara | In progress | 1000000 | Advance Payment,Invoice #1 | September 28, 2023 | December 31, 2024 |  | Yes | 300 000 € in 2023 (+ or - 50k).
Grobmeier Solutions (Log4j) | Mirko | In progress | 596160 | Advance Payment (59.616,00),log4j Milestone #1,log4j Milestone #2,log4j Milestone #3,log4j Milestone #4,log4j Milestone #5,log4j Milestone #6,log4j Milestone #7,log4j Milestone #8,log4j Milestone #9,log4j Milestone #10,log4j Milestone #11,log4j Milestone #12,log4j Milestone #13,log4j Milestone #14,log4j Milestone #15,log4j Milestone #16,log4j Milestone #18,log4j Milestone #19,log4j Milestone #20,log4j Milestone #21,log4j Milestone #22,log4j Milestone #23,log4j Milestone #24,log4j Milestone #25,log4j Milestone #26,log4j Milestone #17,log4j Milestone #27,log4j Milestone #28,log4j Milestone #29,log4j Milestone #30 | August 11, 2023 | December 31, 2024 | May23 | No
Igalia S. L. (Web Development Libraries) | Tara | In progress | 454350 | igalia 2023 2023-371A,igalia 2023-468A | October 19, 2023 | December 31, 2024 |  | Yes | ±127010 EUR for 2023 (7 DEC Update: 5k less)
ISRG (Prossimo) | Fiona | In progress | 1557468.48 | Rustls A. ,Rustls B. ,Rustls C. ,Decoder A. ,Decoder B. ,Trust-DNS A. ,Trust-DNS B. ,Trust-DNS C. | June 7, 2023 | December 31, 2024 | April23 | Yes
learningProof AG (activity pub) | Tara | In progress | 152000 | AP Milestone 1,AP Milestone 2,AP Milestone 3 | October 10, 2023 | August 31, 2024 |  | Yes | Confirmed on track.
Les Bonnes Resolutions (Debian Rust/Coreutils) | Mirko | In progress | 99060 | Milestone #1.1,Milestone #1.2,Milestone #2.1,Milestone #2.2,Milestone #3.2,Milestone #3.3,Milestone #3.1,Milestone #4.1,Milestone #5.1,Milestone #4.3,Milestone #5.2,Milestone #4.2,Milestone #5.3,Milestone #6.1,Milestone #6.2,Milestone #7.1,Milestone #7.2,Milestone #7.3 | October 6, 2023 | December 31, 2023 |  | No
NLNet Labs (domain) | Tara | In progress | 993600 | domain A1,domain A2,domain A3,domain B1,domain B2,domain B3,domain C1,domain C2,domain D1,domain D2 | October 25, 2023 | December 31, 2024 |  | Yes | On track
NumFocus (Fortran (2023)) | Mirko | In progress | 612000 | Milestone #T1,Milestone #T2,Milestone #T3,Milestone #T4,Milestone #T5,Milestone #T6,Milestone #T7,Milestone #T8,Milestone #T9,Advance Payment 68.000 EUR | July 17, 2023 | December 31, 2024 | May23 | No
OpenJS Foundation | Fiona | In progress | 874940 | OpenJS Milestone #1 ,OpenJS Milestone #2 ,OpenJS Milestone #3 ,OpenJS Milestone #4 ,OpenJS Milestone #6 ,OpenJS Milestone #5,OpenJS Milestone #7 | April 19, 2023 | December 31, 2024 | April23 | No
OpenTeams (OpenBLAS) | Abigail | In progress | 263000 | OpenBLAS Milestone #1,OpenBLAS Milestone #2,OpenBLAS Milestone #3,OpenBLAS Milestone #5,OpenBLAS Milestone #6,OpenBLAS Milestone #7,OpenBLAS Milestone #4,Vorauszahlung €52,600.00 | April 19, 2023 | December 31, 2024 | April23 | Yes
PEP AG (SequoiaPGP (2023)) | Mirko | In progress | 900000 | Advance Payment SequoiaPGP (90000),Invoice September 23,Invoice October 23,Invoice November 23,Invoice December 23,Invoice 2024 Jan,Invoice 2024 Feb,Invoice 2024 Mar,Invoice 2024 Apr,Invoice 2024 May,Invoice 2024 Jun,Invoice 2024 Jul,Invoice 2024 Aug,Invoice 2024 Sep,Invoice 2024 Oct,Invoice 2024 Nov,Invoice 2024 Dec,Invoice July/Aug/Sep 23 | September 13, 2023 | December 31, 2024 | May23 | Yes
php foundation | Abigail | In progress | 205000 |  | November 17, 2023 | December 31, 2024 |  | No
PILOT Jason A. Donenfeld (Wireguard) | Tara | Closed | 209000 | Wireguard SP-2022-01,Wireguard SP-2023-03,Wireguard Advance SP-2023-01,Wireguard Advance Contract Signing | October 18, 2022 | May 18, 2023 | Pilot Round | Yes | -
PILOT NumFocus (Fortran) | Fiona | Closed | 200000 | Invoice #1,Invoice #2,Invoice #3 Advance Payment,Invoice #4,Invoice #5 | November 10, 2022 | June 10, 2023 | Pilot Round | Yes
PILOT Phoenix R&D GmbH (OpenMLS (Raphael)) | Fiona | Closed | 195000 | Invoice #1,Advance Payment without invoice | October 12, 2022 | May 12, 2023 | Pilot Round, easy | Yes | -
PILOT Pibit AG (Sequoia PGP) | Fiona | Closed | 200000 | Invoice #1,Invoice #2 | November 21, 2022 | June 21, 2023 | Non-responsive, Pilot Round | Yes | -
PILOT Proton AG (OpenPGP.js (Daniel)) | Fiona | Closed | 172860 |  | October 25, 2022 | May 25, 2023 | Pilot Round, easy | Yes | -
PILOT Route Server Foundation (OpenBGPd) | Tara | Closed | 200000 | RSSF Advance Contract Signing,RSSF 2023-005,RSSF 2023-0003,RSSF 2023-0012,RSSF 2023-006,RSSF 2023-004 | October 18, 2022 | May 18, 2023 | Pilot Round | Yes | -
PILOT Ruby Central Inc. (RubyGems & Bundler (André)) | Tara | Closed | 200000 | bundlr/rubygems Advance Contract Signing,bundlr/Rubygems Payment #1,bundlr/Rubygems Invoice STF001-03,bundlr/Rubygems Advance #2 | October 21, 2022 | May 21, 2023 | Pilot Round | Yes | -
PILOT Theo de Raadt (OpenSSH) | Fiona | Expired (Not Closed) | 200000 | OpenSSH 2022-1,OpenSSH 2023-1 ,Advance Contract Signing | October 17, 2022 | May 17, 2023 | Hard, Pilot Round | No | Following up with Eric and Eva
PILOT WolfSSL (curl (Daniel Stenberg)) | Tara | Closed | 195000 | Curl Invoice 11312,Curl Advance | October 21, 2022 | May 21, 2023 | Pilot Round | Yes | -
http://prefix.dev GmbH (mamba) | Abigail | In progress | 349875 |  | October 6, 2023 | August 31, 2024 |  | No
QOS.ch Sárl (logback) | Abigail | In progress | 180000 | logback Milestone #01 ,logback Milestone #02,logback Milestone #3,logback Milestone #4,logback Milestone #5,logback Milestone #6,logback Milestone #7,logback Milestone #8,logback Milestone #9,logback Milestone #10,Vorauszahlung (18,000 Euro) | April 19, 2023 | December 31, 2024 | April23 | No
Ruby Central Inc. (RubyGems 2023) | Abigail | In progress | 668400 |  | August 8, 2023 | December 31, 2024 | May23 | Yes
Software Freedom Conservancy (reproducible builds) | Tara | In progress | 353430 |  | November 6, 2023 | December 31, 2024 |  | No | Waiting on Payment schedule from them
The Linux Foundation (yocto) | Mirko | In progress | 769829.4 | #Milestone #1,#Milestone #2,#Milestone #3 | July 27, 2023 | April 30, 2024 | May23 | Yes
Trail of Bits (PyPi_Sigstore) | Tara | In progress | 1056672.77 | ToB Milestone 1.2,ToB Milestone 2.1,ToB Milestone 3.2,ToB Milestone 4.1,ToB Milestone 5,ToB Milestone 1.1,ToB Milestone 1.3,ToB Milestone 2.2,ToB Milestone 4.2,ToB Milestone 3.1 | April 18, 2023 | June 30, 2024 | April23 | Yes | Updated table in Prognose
TweedeGolf (Pendulum) | Abigail | In progress | 449850 | Milestone #5,Milestone #1,Milestone #3,Milestone #4,Milestone #6,Milestone #2,Milestone #7,Milestone #8,Milestone #9 | July 12, 2023 | November 30, 2024 | May23 | Yes
Open Source Collective (PHP Ecosystem) | Abigail | In progress | 205000 | Invoice #1,Invoice #2,Invoice #3,Invoice #4 | November 17, 2023 | December 31, 2024 |  | No